## Pharmacy Retail
Project Description:
Schedule:
To Do:

## Radiology
Project Description: | An interface needs to be developed by Cerner to bring in medical x-ray images from the radiology system (see Saul Duenas for details) into PEMRS.
Ammendment: | 10
Schedule: | Awaiting approval of ammendment 10.
To Do: | Review medical x-ray system with Saul, see if there's anything else we need to do before Cerner starts the interface.

## Supply Chain
Issues | Action Item
Cerner unable to connect to Cardinal server | Follow up with Isaac about Guillermo's meeting with Cardinal. Bring up slow communication with Scott?
CareFusion need to access probation server. | Julio coordinating communication between Security, ISD and CareFusion. Security says SSL VPN token or bust. CareFusion says that won't work, requests webex session when changes are needed.

## Telcor
Assigned | Task | Status | Issue | Action Item
Julio | Establish connectivity with clinitek machines
Carol | Coordinate with users to finalize workflow. Develop requirements document.